## Sheet1
S.No | Module | Planned Time | Start Time | End Time | Completed Time | Difference
1 | Reading Document and Excel File Preparation | 20 mins | 9.10 am | 9.30 am | 20 mins | 0
2 | PersonalDetails Class | 10 mins | 9.30 am | 9.40 am | 10 mins | 0
3 | Iwallet Manager Interface | 5 mins | 9.40 am | 9.45 am | 5 mins | 0
4 | User Registration Class | 10 mins | 9.45 am | 9.53 am | 8 mins | 2 mins
5 | Room Details Class | 10 mins | 9.53 am | 10.01 am | 8 mins | 2 mins
6 | Room Selection Class | 15 mins | 10.01 am | 10.15 am | 14 mins | 1 min
7 | Booking Details Class | 10 mins | 10.15 am | 10.23 am | 8 mins | 2 mins
8 | Adding Default Details | 15 mins | 10.23 am | 10.44 am | 21 mins | 6 mins
9 | Main menu | 15 mins | 10.44 am | 10.54 am | 10 mins | 5 mins
10 | Registration menu | 15 mins | 10.54 am | 11.03 am | 9 mins | 6 mins
11 | Login menu | 10 mins | 11.03 am | 11.09 am | 6 mins | 4 mins
12 | Submenu | 10 mins | 11.09 am | 11.19 am | 10 mins | 0
13 | View customer profile | 5 mins | 11.23 am | 11.30 am | 7 mins | 2 mins
14 | Book Room | 40 mins | 1.38 pm | 2.54 pm | 76 mins | 36 mins
15 | Modify Booking | 45 mins | 3.09 pm | 4.19 pm | 70 mins | 25 mins
16 | Cancel Booking | 15 mins | 2.54 pm | 3.09 pm | 15 mins | 0
17 | Booking History | 10 mins | 12.08 pm | 12.25 pm | 17 mins | 7 mins
18 | Wallet Recharge | 5 mins | 12.25 pm | 12.30 pm | 5 mins | 0
19 | Show WalletBalance | 5 mins | 12.30 pm | 12.32 pm | 2 mins | 3 mins
20 | CustomList creation | 25 mins | 4.20 pm | 4.50 pm | 30 mins | 5 mins
21 | CSV file Integration | 25 mins | 4.50 pm | *** | 10 mins | Not